EVERY TREE FOR HOPE REFORESTATION & COMMUNITY IMPACT PLATFORM PROJECT PROPOSAL Mobile Application Design, Development & Delivery A cross-platform iOS and Android application built in React Native, extending the existing Every Tree for Hope platform with volunteer task management, offline field data capture and trilingual support.

| PROPOSAL REFERENCE | ETFH-MOB-2026-001 |
| --- | --- |
| VERSION | 1.0 |
| DATE OF ISSUE | 21 July 2026 |
| VALID UNTIL | 20 August 2026 (30 days from issue) |
| PREPARED FOR | Full Name |
| PREPARED BY | Every Tree For a Hope |
| CONTACT | mohammadozairkhurami@gmail.com · +93 781668357 |
| ENGAGEMENT TYPE | Fixed-price, fixed-scope |
| TOTAL INVESTMENT | USD 700.00 |

This document is commercial-in-confidence. It is submitted for the sole purpose of evaluating the proposed engagement and should not be disclosed to third parties without written consent.

SECTION 1

Executive Summary

Every Tree for Hope operates a mature web platform built on Laravel 12, serving trilingual content across English, Dari and Pashto, with a comprehensive administrative back office. This proposal covers the design and delivery of a companion native mobile application for iOS and Android, built in React Native, that extends the organisation's reach into the field.

The mobile application is not a repackaged website. It introduces capability the current platform cannot provide: a volunteer task management system that assigns, tracks and verifies field work; offline-first data capture so volunteers can record planting activity in areas without connectivity; and GPS-tagged photographic evidence that strengthens the organisation's impact reporting and donor accountability.

Why this matters now

Operational efficiency. Volunteer coordination currently depends on manual, off-platform communication. The app turns it into a managed, auditable workflow.

Data quality. Field data reaches the system at the moment of work, with location and photo evidence attached, rather than being reconstructed later.

Donor confidence. Verified, timestamped, geo-located planting records materially strengthen grant applications and donor reporting.

Reach. A mobile presence in Dari and Pashto meets rural Afghan communities on the device they actually use.

Proposal at a glance

| Item | Commitment |
| --- | --- |
| Platforms | iOS and Android, from a single React Native codebase |
| Core technology | React Native (Expo), TypeScript, Laravel REST API |
| New capability | Volunteer task management, offline capture, GPS check-in, push notifications |
| Languages | English, Dari (RTL), Pashto (RTL) |
| Backend | New authenticated API layer added to the existing Laravel platform |
| Duration | 4 weeks from signed acceptance |
| Engagement model | Fixed price, fixed scope |
| Total investment | USD 700.00 |

SECTION 2

Background & Technical Rationale

2.1 The existing platform

Every Tree for Hope runs a server-rendered Laravel 12 monolith with a Filament 5 administrative panel. It manages 22 domain entities across 36 database tables, including planting events with survival-rate tracking, expenditure records, supporter and sponsorship data, community tree requests, volunteer involvement requests and a moderated community wall. Authorisation is governed by a role-based access control model spanning approximately 125 discrete permissions.

This is a solid foundation. The mobile application is designed to build directly on it rather than duplicate it — the same database, the same permission model, the same administrative workflows.

2.2 The critical technical gap

Building this API layer is essential, non-optional work, and it is included in the quoted price. This is stated explicitly because it is invisible from the outside and is a common source of mid-project budget disputes. The work comprises a versioned REST API, token authentication via Laravel Sanctum, resource transformers for each exposed entity, rate limiting, and reuse of the existing policy classes so that mobile clients inherit the same authorisation rules already enforced in the admin panel.

2.3 Why React Native

| Consideration | Rationale |
| --- | --- |
| Single codebase | One codebase serves both iOS and Android, roughly halving build and maintenance cost against two native applications — decisive at this budget. |
| Mature RTL support | React Native handles right-to-left layout at the framework level, which is essential for Dari and Pashto. |
| Offline capability | A well-established local-storage and synchronisation ecosystem supports field use without connectivity. |
| Talent availability | React Native developers are widely available, so the organisation is not locked to a single supplier for future maintenance. |
| Over-the-air updates | Content and logic fixes can be shipped without a full app-store review cycle. |

SECTION 3

Objectives & Success Criteria

The engagement is measured against defined, verifiable outcomes rather than subjective impressions. Each objective below carries a success criterion that will be tested at acceptance.

| Ref | Objective | Success criterion |
| --- | --- | --- |
| O-1 | Deliver a published mobile application on both major platforms | Application approved and live on Apple App Store and Google Play |
| O-2 | Enable managed volunteer task assignment and completion | A coordinator can assign a task; a volunteer can receive, complete and evidence it in-app |
| O-3 | Support field data capture without connectivity | Records created offline persist and synchronise automatically on reconnection |
| O-4 | Provide full trilingual operation | All interface text renders correctly in English, Dari and Pashto, with correct RTL layout |
| O-5 | Integrate securely with the existing platform | All data flows through the authenticated API; existing permission rules are enforced |
| O-6 | Transfer complete ownership to the organisation | Source code, store accounts, documentation and credentials handed over in full |

3.2 Out-of-the-box measurement

Basic, privacy-respecting usage analytics are included so that the organisation can evidence adoption to donors: installation counts, active volunteers, tasks completed and records synchronised. No personal data is sold, shared or used for advertising.

SECTION 4

Scope of Work

4.1 Module A — Volunteer Task Management

The principal new capability, and the module that distinguishes the app from the existing website.

Task assignment. Coordinators create tasks from the admin panel and assign them to individual volunteers or teams, with title, description, location, due date and priority.

Volunteer task list. Volunteers see a personal task list segmented into assigned, in progress, submitted and completed states.

Status workflow. Tasks move through a defined lifecycle: assigned → accepted → in progress → submitted → verified or returned for correction.

Evidence capture. Completion requires evidence — photographs, a short note, and an optional GPS location captured at the point of submission.

Verification. A coordinator reviews submitted work in the admin panel and either verifies it or returns it with comments.

Personal history. Each volunteer sees their own contribution record: tasks completed, trees planted and hours logged.

4.2 Module B — Field Data Capture (offline-first)

Planting records. Volunteers record planting activity in the field: tree counts, species, location and photographs.

Offline queue. All capture works fully offline. Records queue locally and synchronise automatically when connectivity returns, with clear pending and synced indicators.

Maintenance visits. Follow-up visits can be logged against an existing planting event, feeding the platform's existing survival-rate tracking.

Image handling. Photographs are compressed on-device before upload to respect limited mobile data.

4.3 Module C — Public Content

Events. Browse planting events with images, location, tree counts and survival data.

Upcoming events. View and register interest in scheduled activities.

Voices of Nature. Read, post, like and comment on the community wall, mirroring existing moderation rules.

Careers. Browse vacancies and submit applications with a document attachment.

Media. Video story library and image galleries.

Organisational pages. Financial transparency report, sponsorship packages, partners, team and FAQ.

4.4 Module D — Engagement & Submissions

In-app forms. Community planting requests, get-involved enquiries and contact messages, submitted directly from the app into the existing review workflows.

Push notifications. Coordinators can notify volunteers of new tasks, event reminders and approvals.

4.5 Module E — Platform Foundations

Trilingual interface. English, Dari and Pashto, with correct right-to-left layout and appropriate Arabic-script typefaces.

Authentication. Secure login for volunteers and staff using token-based authentication, honouring the platform's existing roles and permissions.

Design system. A visual language consistent with the existing brand palette and typography.

Accessibility. Scalable text, sufficient colour contrast and screen-reader labelling on primary flows.

4.6 Module F — Backend API Layer

API endpoints. Versioned REST API added to the existing Laravel application.

Token authentication. Laravel Sanctum token issuance, refresh and revocation.

Task schema. New database tables and admin screens for the task management module.

Security controls. Rate limiting, request validation and reuse of existing policy classes.

SECTION 5

Exclusions & Assumptions

5.1 Explicitly out of scope

The following are not included. They are listed plainly so that expectations are aligned from the outset; each can be quoted separately if required.

| Excluded item | Note |
| --- | --- |
| In-app payment processing | Donations route to the existing third-party provider. No card data is handled. |
| Native iOS or Android rewrites | Delivery is React Native only. |
| Third-party account fees | Apple Developer (USD 99/year) and Google Play (USD 25 one-off) are paid by the organisation. |
| Ongoing hosting and infrastructure | Existing server, domain and database costs remain the organisation's responsibility. |
| Content creation and translation | Dari and Pashto translation strings are supplied by the organisation. |
| Real-time chat or messaging | Not included; available as a future phase. |
| Post-warranty maintenance | Beyond the warranty in Section 10, support is by separate agreement. |

5.2 Assumptions

The organisation provides timely access to the existing codebase, staging server and database.

A single named person is empowered to approve designs, review milestones and sign off deliverables.

Feedback on each milestone is returned within five working days.

Translated interface text for Dari and Pashto is supplied by the organisation before the localisation milestone.

Existing brand assets — logo, colour palette, imagery — are made available in usable formats.

SECTION 6

Technical Approach

5.3 Proposed technology stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Framework | React Native (Expo) | Cross-platform application runtime |
| Language | TypeScript | Static typing to reduce defects before runtime |
| Navigation | React Navigation | Screen routing and deep linking |
| Server state | TanStack Query | Data fetching, caching and background refresh |
| Local state | Zustand | Lightweight application state |
| Offline store | SQLite / MMKV | Durable local persistence and sync queue |
| Forms | React Hook Form + Zod | Form handling with schema validation |
| HTTP client | Axios | API transport with token interceptors |
| Localisation | i18next | Trilingual strings with RTL handling |
| Notifications | Expo Notifications | Push delivery on both platforms |
| Media | Expo Camera / ImagePicker | Photo capture and on-device compression |
| Location | Expo Location | GPS tagging for task and planting evidence |
| Backend API | Laravel 12 + Sanctum | Authenticated REST layer on the existing platform |
| Testing | Jest + React Native Testing Library | Automated unit and component tests |
| Distribution | EAS Build & Submit | Store builds and submission pipeline |

5.4 Architecture

The mobile application is a client of the existing platform. No data is duplicated and no second source of truth is introduced.

MOBILE CLIENT React Native app — iOS & Android · offline cache · local sync queue ▼ TRANSPORT HTTPS · Sanctum bearer token · request validation · rate limiting ▼ API LAYER (new) Versioned REST endpoints · resource transformers · existing policy classes ▼ EXISTING PLATFORM Laravel 12 · Eloquent models · RBAC · Filament admin panel ▼ DATA MySQL 8.0 · file storage · Redis cache & queue

5.5 Offline synchronisation strategy

Field connectivity cannot be assumed. Every write action is recorded to a local queue with a client-generated identifier and a timestamp, then replayed against the API when the device reconnects. Conflicts are resolved server-side on a last-write-wins basis with the server retaining an audit trail, and the user is shown a clear per-record status of pending, syncing, synced or failed. Failed records are retained and retryable — data is never silently discarded.

5.6 Quality assurance

Automated unit and component tests covering task workflow logic and the offline sync queue.

Manual test passes on physical Android and iOS devices, including low-end Android hardware representative of the target user base.

Explicit RTL verification for Dari and Pashto on every screen.

Airplane-mode testing of the full offline capture and synchronisation cycle.

SECTION 7

Deliverables

| Ref | Deliverable | Format |  |
| --- | --- | --- | --- |
| D-1 | React Native application source code | Git repository, full history |  |
| D-2 | Laravel API layer source code | Merged into existing repository |  |
| D-3 | Published Android application | Live on Google Play |  |
| D-4 | Published iOS application | Live on Apple App Store |  |
| D-5 | UI design screens | Figma file, editable |  |
| D-6 | API documentation | Endpoint reference with request/response examples |  |
| D-7 | Administrator guide | Task creation, assignment and verification |  |
| D-8 | Volunteer user guide | Illustrated, in English |  |
| D-9 | Build and release runbook | Step-by-step for future releases |  |
| D-10 | Store assets | Icons, screenshots, listing copy |  |
| D-11 | Credential handover | All accounts and keys transferred to the organisation |  |
| D-12 | Handover walkthrough | Live session, recorded |  |
| OWNERSHIP On receipt of the final payment, all intellectual property in the delivered source code, designs and documentation transfers to Every Tree for Hope in full. There is no licence fee, no ongoing royalty, and no vendor lock-in. The organisation is free to engage any developer for future work. |  |  |

SECTION 8

Timeline & Milestones

Twelve weeks from signed acceptance and receipt of the initial payment. Each milestone concludes with a demonstrable output for review.

| Phase | Days | Activity | Milestone output |
| --- | --- | --- | --- |
| 1. Discovery & design | 3-5 | Requirements confirmation, task-workflow definition, UI design | Approved screen designs |
| 2. Backend API | 3-4 | REST endpoints, Sanctum auth, task schema, admin screens | Working API + documentation |
| 3. App foundations | 6-8 | Navigation, authentication, design system, trilingual setup | Installable build, login working |
| 4. Content modules | 6-8 | Events, voices, careers, media, forms, donations | Public features complete |
| 5. Task management | 3-5 | Task lifecycle, evidence capture, offline sync, notifications | Volunteer workflow demo |
| 6. QA & hardening | 2-4 | Device testing, RTL verification, offline testing, fixes | Release-candidate build |
| 7. Launch & handover | 3-4 | Store submission, documentation, training session | Live apps + full handover |

SECTION 9

Warranty, Support & Risk

5.7 Warranty

A 60-day defect warranty applies from the date of store publication. Any defect where the application does not behave as described in this proposal will be corrected at no charge. The warranty covers defects in delivered work; it does not cover new features, changes requested after acceptance, faults arising from third-party service changes, or issues caused by modifications made by others.

5.8 Optional ongoing support

Not included in this proposal, offered for future consideration:

| Option | Includes | Indicative |
| --- | --- | --- |
| Maintenance retainer | OS compatibility updates, dependency patching, minor fixes | Quoted on request |
| Feature development | New modules and enhancements | Quoted per scope |
| Training refresh | Additional sessions for new staff | Quoted on request |

5.9 Risk register

| Risk | Impact | Mitigation |
| --- | --- | --- |
| App-store rejection | Launch delay | Guidelines reviewed during design; store assets prepared early; resubmission included |
| Translation not supplied on time | Localisation delay | Requirement flagged at kick-off; English-only build can ship first if necessary |
| Scope expansion during build | Cost and schedule pressure | Written variation process in Section 5.3 |
| Delayed client feedback | Timeline slip | Five-working-day review windows agreed at kick-off |
| Existing platform constraints | Rework in API layer | Codebase reviewed in advance; API designed around current schema |
| Low-end device performance | Poor field experience | Testing on representative low-end Android hardware |

SECTION 11

Acceptance

To proceed, please sign below and return a copy. Work commences on receipt of the signed proposal and the initial payment.

6.1 Agreement

By signing, both parties agree to the scope defined in Section 4, the exclusions in Section 5, the deliverables in Section 7, the timeline in Section 8, and the fee and payment schedule in Section 9. This proposal, once signed, forms the agreement between the parties.

| FOR EVERY TREE FOR HOPE Name Position Signature Date | FOR [YOUR COMPANY NAME] Name Position Signature Date |
| --- | --- |

NEXT STEPS 1. Review this proposal and raise any questions. 2. Confirm the scope in Section 4 reflects your priorities. 3. Sign and return. 4. Kick-off meeting scheduled within five working days of signature.

Thank you for the opportunity to contribute to the work of Every Tree for Hope.